## 8.17 Regression Plan
ERA 8.17 regression test (2022/06/28 --2022/ )
NO. | Products/Platforms | Sustaining Products and Platforms: | Start Date | Target complete date | Status | Remark | Complete rate | Owner
1 | Products | Monza (EX92xx i.e. rebranded MPC-10/SCBE3) | 2022-07-09 |  | NO HW |  |  | Sarah
2 |  | Ferrari SCBE3/ MPC10-15 and MPC10-10 including DVT | 2022-07-09 |  | NO HW |  |  | Flank
3 |  | Redbull (SFB3/MPC11) | 2022-07-09 | 2022-07-30 | On-going | MPC11 done |  | Tracy
4 |  | Bulwark (SRX – IOC4 /SPC3, SCB4) | 2022-07-09 | 2022-07-30 | NO HW |  |  | Sarah
5 | Platforms | SRX-Series: SRX4600, SRX5400, SRX5600, SRX5800 | 2022-07-09 | 2022-07-30 | NO HW | SRX5800 SAT done. SRX4600 not available in FVN, SRX5400/SRX5600 not available now. |  | Sarah
6 |  | MX-HE: MX240/480/960 (with SCB2 and SCB3) | 2022-07-09 | 2022-07-30 | On-going | MX240 done, MX480 done, MX960 done |  | Sarah
7 |  | MX2K: MX2010/2020 (MPC8/9/10/11, SFB2/SFB3) | 2022-07-09 | 2022-07-30 | On-going | MPC8 done, RE done |  | Tracy
8 |  | MX104: FST/SWTEST and Packout | 2022-07-09 | 2022-07-30 | Close | - MX104 CTO done SWT - MIC-3D-20GE-EH OK - MIC-MACSEC OK - PACKOUT done |  | Michael
9 |  | MX2008 | 2022-07-09 | 2022-07-30 | On-going |  |  | Tracy
10 |  | EX-92xx | 2022-07-09 | 2022-07-30 | Close |  |  | Sarah
Note: use MT-Rainer and regular RE where applicable

## Regression Status Summary
Non-test | Fill "NA" | Testing
Need test | Fill "x" or fill status Testing/Pass/Fail | Pass
Fail
Regression Status: |  | Products/ Platform | PN | PICTEST | FPCTEST | SCBTEST | RE_FCT | RE_FCT2 | SAT | SAT2 | BFT1 | BFT2 | SLT | RIT | DVT | FST_SPARES | SWTEST | PACKOUT | Complete Rate | Pass | Fail | Complete | HW not available
Products | Monza (EX92xx i.e. rebranded MPC-10/SCBE3) | MPC-10 |  | NA | NA | NA | NA | NA | NA | NA | X | x | x | NA | NA | x | NA | NA |  |  |  |  | NO HW
|  | SCBE3 |  | NA | NA | NA | NA | NA | NA | NA | X | x | x | NA | NA | x | NA | NA |  |  |  |  | NO HW
| Ferrari SCBE3/ MPC10-15 and MPC10-10 including DVT | SCBE3 |  | NA | NA | NA | NA | NA | NA | NA | X | x | x | NA | X | x | NA | NA |  |  |  |  | NO HW
|  | MPC10-10 |  | NA | NA | NA | NA | NA | NA | NA | X | x | x | NA | X | x | NA | NA |  |  |  |  | NO HW
|  | MPC10-15 |  | NA | NA | NA | NA | NA | NA | NA | X | x | x | NA | X | x | NA | NA |  |  |  |  | NO HW
| Redbull (SFB3/MPC11) | SFB3 |  | NA | NA | NA | NA | NA | NA | NA | x | Pass | Pass | NA | NA | x | NA | NA
|  | MPC11 |  | NA | NA | NA | NA | NA | NA | NA | Pass | Pass | Pass | NA | NA | x | NA | NA
Platfoms | SRX-Series: SX4600, SRX5400, SRX5600, SRX5800 | SX4600 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | NO HW
|  | SRX5400 |  | NA | NA | NA | NA | NA | x | NA | NA | NA | NA | NA | NA | x |  | NA |  |  |  |  | NO HW
|  | SRX5600 |  | NA | NA | NA | NA | NA | x | NA | NA | NA | NA | x | NA | x |  | NA |  |  |  |  | NO HW
|  | SRX5800 |  | NA | NA | NA | NA | NA | x | NA | NA | NA | NA | x | NA | x |  | NA |  |  |  |  | NO HW
| MX-HE: MX240/480/960 (with SCB2 and SCB3) | MX240-SCBE2 | MX240 | NA | NA | NA | NA | NA | Pass | NA | NA | NA | NA | Pass | NA | Pass | Pass | NA
|  | MX240-SCBE3 | MX240 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Pass |  | NA
|  | MX480-SCBE2 | MX480 | NA | NA | NA | NA | NA | Pass | NA | NA | NA | NA | Pass | NA | Pass | Pass
|  | MX480-SCBE3 | MX480 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | x |  | NA
|  | MX960-SCBE2 | MX960 | NA | NA | NA | NA | NA | Pass | NA | NA | NA | NA | Pass | NA | Pass | Pass | NA
|  | MX960-SCBE3 | MX960 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | x | NA | x |  | NA
| MX2K: MX2010/2020 (MPC8/9/10/11, SFB2/SFB3,RE) | MX2020-MPC11E | 750-086583 | NA | NA | NA | NA | NA | NA | NA | Pass | Pass | Pass | NA | NA | Pass | NA | NA
|  | MX2020-SFB3 | 750-069467 | NA | NA | NA | NA | NA | NA | NA | x | Pass | Pass |  | NA | x | NA | NA
|  | REMX2K-X8-64G-S | 750-055087 | NA | NA | NA | Pass | Pass | Pass | NA | NA | NA | NA | Pass | NA | Pass | NA | NA
|  | REMX2K-X8-128G-S-S | 750-073158 | NA | NA | NA | Pass | Pass | Pass | NA | NA | NA | NA | Pass | NA | Pass | NA | NA
|  | MX2020-MPC8 | 750-054576 | NA | Pass | NA | NA | NA | NA | NA | NA | NA | NA | Pass | NA | Pass | NA | NA
|  | MX2020-SFB2 | [8 empty] | Pass | Pass | x |  | NA | x | NA | NA
|  | MIC-MRAT | 750-055992 | Pass | NA | NA | NA | NA | NA | NA | NA | NA | NA | Pass | NA | Pass | NA | NA
| MX104: FST/SWTEST and Packout | MIC-MACSEC |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Pass | NA | NA
|  | MIC-3D-20G-EH |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Pass | NA | NA
|  | MX104 SPARES |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Pass | NA | NA
|  | MX104 CTO |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Pass | Pass | Pass
| MX2008 | [13 empty] | NA
NA
NA
NA
|  | EX9214 | [6 empty] | Pass | [5 empty] | NA

## Products validation result (hidden)
Products validation result
Script Revision | Script Revision | 8.17
Current script Revision | Current script Revision
Release Area | Release Area | ERA
Switch Date | Switch Date
|  | Test ID | Test Station | RE/CB | Model Number | Part Number | Serial | # of Run | Date | Script Version | Junos version | Console Terminal Port (ctxxyy) | Result | Error code | log file path | Fail message | Total Test Time | PR number | Analysis | feedback from script team | Notepad Hardware
Monza (EX92xx i.e. rebranded MPC-10/SCBE3) | MPC-10BFT1 | BFT1 | BFT1 |  | MPC-10
| MPC-10BFT2 | BFT2 | BFT2 |  | MPC-10
| MPC-10SLT | SLT | SLT |  | MPC-10
| MPC-10FST_S | FST_S | FST_S |  | MPC-10
| SCBE3BFT1 | BFT1 | BFT1 |  | SCBE3
| SCBE3BFT2 | BFT2 | BFT2 |  | SCBE3
| SCBE3SLT | SLT | SLT |  | SCBE3
| SCBE3FST_S | FST_S | FST_S |  | SCBE3
Ferrari SCBE3/ MPC10-15 and MPC10-10 including DVT | SCBE3BFT1 | BFT1 | BFT1 |  | SCBE3
| SCBE3BFT2 | BFT2 | BFT2 |  | SCBE3
| SCBE3SLT | SLT | SLT |  | SCBE3
| SCBE3FST_S | FST_S | FST_S |  | SCBE3
| SCBE3DVT | DVT | DVT |  | SCBE3
| MPC10-10BFT1 | BFT1 | BFT1 |  | MPC10-10
| MPC10-10BFT2 | BFT2 | BFT2 |  | MPC10-10
| MPC10-10SLT | SLT | SLT |  | MPC10-10
| MPC10-10FST_S | FST_S | FST_S |  | MPC10-10
| MPC10-10DVT | DVT | DVT |  | MPC10-10
| MPC10-15BFT1 | BFT1 | BFT1 |  | MPC10-15
| MPC10-15BFT2 | BFT2 | BFT2 |  | MPC10-15
| MPC10-15SLT | SLT | SLT |  | MPC10-15
| MPC10-15FST_S | FST_S | FST_S |  | MPC10-15
| MPC10-15DVT | DVT | DVT |  | MPC10-15
Redbull (SFB3/MPC11) | SFB3BFT1 | BFT1 | BFT1 |  | SFB3
| SFB3BFT2 | BFT2 | BFT2 |  | SFB3 | 750-069467 | CARF1892 | [5 empty] | Pass |  | /opt/JMTF/Logs/FXVN/2022/July/BFT2/560264097a9b401730f6514
| SFB3SLT | SLT | SLT |  | SFB3
| SFB3FST_S | FST_S | FST_S |  | SFB3
| MPC11BFT1 | BFT1 | BFT1 |  | MPC11 | 750-072571 | EBAB5072 |  |  |  | 19.3I-20201201_dev_mfg_193_unified.0.1457 |  | Pass |  | /opt/JMTF/Logs/FXVN/2022/July/BFT1/7f0431055005c73767a0791
| MPC11BFT2 | BFT2 | BFT2 |  | MPC11 | [7 empty] | Pass |  | /opt/JMTF/Logs/FXVN/2022/July/BFT2/560264097a9b401730f6514
| MPC11SLT | SLT | SLT |  | MPC11 | 750-086583 | EBAB5077 | [5 empty] | Pass |  | /opt/JMTF/Logs/FXVN/2022/July/SLT/04063fb1967534012708a01
| MPC11FST_S | FST_S | FST_S |  | MPC11

## Products_issue summary (hidden)
Item | Report Date | PR Number | Issue Description | Platform | TID | configuration | script version | Originator | Responsible | Status | PR Category | Comments

## Platforms validation result
Platforms validation result
Script Revision | Script Revision | 8.17
Current script Revision | Current script Revision
Release Area | Release Area | ERA
Switch Date | Switch Date
|  | Test ID | Test Station | Model Number | SCB Type | Part Number | Serial | Date | Script Version | Junos version | Console Terminal Port (ctxxyy) | Result | Error code | log file path | Fail message | Total Test Time | PR number | Analysis | feedback from script team | Notepad Hardware
SRX-Series: SX4600, SRX5400, SRX5600, SRX5800 | SX4600_NA_ | NA |  | SX4600 |  | NA
| SRX5400__ |  |  | SRX5400
| SRX5600__ |  |  | SRX5600
| SRX5600__ |  |  | SRX5600
| SRX5600__ |  |  | SRX5600
| SRX5600__ |  |  | SRX5600
| SRX5800_SAT_ | SAT | SAT | SRX5800 |  | SRX5800 | JN127390BAGA | 20220713.0232 | 8.17.0.19 | JUNOS-15.1-20180413_mfg_15q1_srx_x49.0 |  | Pass |  | https://fvnmfg1.juniper.net/jmtf_logs/FXVN/2022/July/SAT/62d736f144065010585703a/ |  | 1
| SRX5800_RIT_ | RIT | RIT | SRX5800
| SRX5800_FST_ | FST | FST_S | SRX5800
| SRX5800_SWT_ | SWT | SWTEST | SRX5800
MX-HE: MX240/480/960 (with SCB2 and SCB3) | MX240_SAT_SCBE2 | SAT | SAT | MX240 | SCBE2 | MX240 | JN1270FEDAFC | 20220717.0209 | 8.17.0.23 | JUNOS-17.4-20210211_mfg_174_unified_prod.0 |  | Pass |  | https://fvnmfg1.juniper.net/jmtf_logs/FXVN/2022/July/SAT/569199800af598514066370/ |  | 2.18
| MX240_RIT_SCBE2 | RIT | RIT | MX240 | SCBE2 | MX240 | JN1270FEDAFC | 20220718.2244 | 8.17.0.24 | 17.4-20210211_mfg_174_unified_prod.0 |  | Pass |  | /opt/JMTF/Logs/FXVN/2022/July/RIT/005013c30015a5458016f19 |  | 10.76
| MX240_FST_SCBE2 | FST | FST_S | MX240 | SCBE2 | MX240 | JN1270FEDAFC | 20220719.2138 | 8.17.0.24 | 17.4-20210211_mfg_174_unified_prod.0 |  | Pass |  | /opt/JMTF/Logs/FXVN/2022/July/FST_SPARES/05144fa5530228121505006 |  | 1.41
| MX240_SWT_SCBE2 | SWT | SWTEST | MX240 | SCBE2 | MX240 | JN1270FEDAFC | 20220720.012 | 8.17.0.24 | 20.4R3.8 |  | Pass |  | /opt/JMTF/Logs/FXVN/2022/July/SWTEST/80f4619300150556402a848 |  | 1.46
| MX480_SAT_SCBE2 | SAT | SAT | MX480 | SCBE2 | MX480 | JN1270FD9AFB | 20220711.2315 | 8.17.0.19 | JUNOS-17.4-20210211_mfg_174_unified_prod.0 |  | Pass |  | https://fvnmfg1.juniper.net/jmtf_logs/FXVN/2022/July/SAT/0140a3505c1f65607526053/ |  | 3.52
| MX480_RIT_SCBE2 | RIT | RIT | MX480 | SCBE2 | MX480 | JN1273D6EAFB | 20220712.0351 | 8.17.0.19 | JUNOS-17.4-20201119_mfg_174_unified_prod.0 |  | Pass |  | https://fvnmfg1.juniper.net/jmtf_logs/FXVN/2022/July/RIT/707705605916425a70048fb/ |  | 8.33
| MX480_FST_SCBE2 | FST | FST_S | MX480 | SCBE2 | MX480 | JN12743C2AFB | 20220712.0532 | 8.17.0.19 | JUNOS-17.4-20201119_mfg_174_unified_prod.0 |  | Pass |  | https://fvnmfg1.juniper.net/jmtf_logs/FXVN/2022/July/FST_SPARES/50c6f50737a404670870081/ |  | 1.37
| MX480_SWT_SCBE2 | SWT | SWTEST | MX480 | SCBE2 | MX480 | JN1271BE2AFB | 20220712.1941 | 8.17.0.19 | JUNOS-64-20.4R3.8 |  | Pass |  | https://fvnmfg1.juniper.net/jmtf_logs/FXVN/2022/July/SWTEST/6555f2370a04690627b0431/ |  | 1.25
| MX960_SAT_SCBE2 | SAT | SAT | MX960 | SCBE2 | MX960 | JN1273877AFA | 20220710.022 | 8.17.0.19 | JUNOS-17.4-20210211_mfg_174_unified_prod.0 |  | Pass |  | https://fvnmfg1.juniper.net/jmtf_logs/FXVN/2022/July/SAT/34571311091fa60030409a4/ |  | 3.55
| MX960_RIT_SCBE2 | RIT | RIT | MX960 | SCBE2 | MX960 | JN127274AAFA | 20220717.0314 | 8.17.0.23 | JUNOS-17.4-20201119_mfg_174_unified_prod.0 |  | Pass |  | https://fvnmfg1.juniper.net/jmtf_logs/FXVN/2022/July/RIT/a0047004814f07a20280156/ |  | 8.62
| MX960_FST_SCBE2 | FST | FST_S | MX960 | SCBE2 | MX960 | JN127274AAFA | 20220718.0909 | 8.17.0.23 | 17.4-20201119_mfg_174_unified_prod.0 |  | Pass |  | /opt/JMTF/Logs/FXVN/2022/July/FST_SPARES/53710068a00113df4710018
| MX960_SWT_SCBE2 | SWT | SWTEST | MX960 | SCBE2 | MX960 | JN127274AAFA | 20220718.1334 | 8.17.0.23 | 20.4R3.8 |  | Pass |  | /opt/JMTF/Logs/FXVN/2022/July/SWTEST/9830a2800c6403645110f37 |  | 1.44
MX2K: MX2010/2020 (MPC8/9/10/11, SFB2/SFB3,RE) | MPC8_FPCTEST_ | FPCTEST | FPCTEST | MPC8 |  | 750-054576 | CASN7531 | 20220719.1735 | 8.17.0.24 | 17.4-20201119_MFG_174_unified_prod.0 | ct1324 | pass |  | /opt/JMTF/Logs/FXVN/2022/July/FPCTEST/1041900048a8255fd626016 |  | 9hours28minutes
| MPC8_RIT_ | RIT | RIT | MPC8 |  | 750-054576 | CASN7531 | 20220718.1014 | 8.17.0.23 | 17.4-20201119_MFG_174_unified_prod.0 | ct0420 | pass |  | /opt/JMTF/Logs/FXVN/2022/July/RIT/f1645502a80117414000081 |  | 12hours45minutes
| MPC8_FST_S_ | FST_S | FST_SPARES | MPC8 |  | 750-054576 | CASN7531 | 20220719.0501 | 8.17.0.24 | 17.4-20201119_MFG_174_unified_prod.0 | ct0420 | pass |  | /opt/JMTF/Logs/FXVN/2022/July/FST_SPARES/650f706878b0012001114a8 |  | 1hours25minutes
| MPC11_BFT1_ | BFT1 | BFT1 | MPC11 |  | 750-086583 | EBAB5077 | 20220709.1603 | 8.17.0.19 | 19.3I-20201201_dev_mfg_193_unified.0.1457 | ct0422 | pass |  | /opt/JMTF/Logs/FXVN/2022/July/BFT1/1442606b3801f4a65497070 |  | 2hours53minutes
| MPC11_BFT2_ | BFT2 | BFT2 | MPC11 |  | 750-086583 | EBAB5077 | 20220709.1925 | 8.17.0.19 | 19.3I-20201201_dev_mfg_193_unified.0.1457 | ct0415 | pass |  | /opt/JMTF/Logs/FXVN/2022/July/BFT2/560264097a9b401730f6514 |  | 10hours3minutes
| MPC11_SLT_ | SLT | SLT | MPC11 |  | 750-086583 | EBAB5077 | 20220711.0153 | 8.17.0.19 | 19.3I-20201201_dev_mfg_193_unified.0.1457 | ct0415 | pass |  | /opt/JMTF/Logs/FXVN/2022/July/SLT/04063fb1967534012708a01 |  | 5hour35minutes
| SFB2_BFT1_ | BFT1 | BFT1 | SFB2
| REMX2K-X8-128_RE_FCT1_ | RE_FCT1 | RE_FCT1 | REMX2K-X8-128 |  | 750-073158 | CARC2864 | 20220711.1518 | 8.17.0.19 | 17.4-20201119_MFG_174_unified_prod.0 | ct0414 | pass |  | /opt/JMTF/Logs/FXVN/2022/July/RE_FCT/76742515f0040646a850604 |  | 5hours26minutes
| REMX2K-X8-128_RE_FCT2_ | RE_FCT2 | RE_FCT2 | REMX2K-X8-128 |  | 750-073158 | CARC2864 | 20220714.1044 | 8.17.0.19 | 17.4-20201119_MFG_174_unified_prod.0 | ct0414 | pass |  | /opt/JMTF/Logs/FXVN/2022/July/RE_FCT2/037fa017345200954681700 |  | 2hours31minutes
| REMX2K-X8-128_SAT_ | SAT | SAT | REMX2K-X8-128 |  | 750-073158 | CARC2864 | 20220717.135 | 8.17.0.23 | 17.4-20201119_MFG_174_unified_prod.0 | ct1323 | pass |  | /opt/JMTF/Logs/FXVN/2022/July/SAT/0606fa90048005401500930 |  | 14hours40minutes
| REMX2K-X8-128_RIT_ | RIT | RIT | REMX2K-X8-128 |  | 750-073158 | CARC2864 | 20220718.1014 | 8.17.0.23 | 17.4-20201119_MFG_174_unified_prod.0 | ct0420 | pass |  | /opt/JMTF/Logs/FXVN/2022/July/RIT/f1645502a80117414000081 |  | 12hours45minutes
| REMX2K-X8-128_FST_S_ | FST_S | FST_S | REMX2K-X8-128 |  | 750-073158 | CARC2864 | 20220719.0501 | 8.17.0.24 | 17.4-20201119_MFG_174_unified_prod.0 | ct0420 | pass |  | /opt/JMTF/Logs/FXVN/2022/July/FST-S/650f706878b0012001114a8 |  | 1hours25minutes
| MIC_PICTEST_ | PICTEST | PICTEST | MIC |  | 750-055992 | CARS2253 | 20220716.1812 | 8.17.0.23 | 17.4-20201119_MFG_174_unified_prod.0 | ct0421 | pass |  | /opt/JMTF/Logs/FXVN/2022/July/PICTEST/a0017969058596f61083604 |  | 2hours14minutes
| MIC_RIT_ | RIT | RIT | MIC |  | 750-055992 | CARS2253 | 20220718.1014 | 8.17.0.23 | 17.4-20201119_MFG_174_unified_prod.0 | ct0420 | pass |  | /opt/JMTF/Logs/FXVN/2022/July/RIT/f1645502a80117414000081 |  | 12hours45minutes
| MIC_FST_S_ | FST_S | FST_SPARES | MIC |  | 750-055992 | CARS2253 | 20220719.0501 | 8.17.0.24 | 17.4-20201119_MFG_174_unified_prod.0 | ct0420 | pass |  | /opt/JMTF/Logs/FXVN/2022/July/FST_SPARES/650f706878b0012001114a8 |  | 1hours25minutes
| SFB3_BFT2_ | BFT2 | BFT2 | SFB3 |  | 750-069467 | CARF1892 | 20220710.0226 | 8.17.0.19 | 19.3I-20201201_dev_mfg_193_unified.0.1457 | ct0415 | pass |  | /opt/JMTF/Logs/FXVN/2022/July/BFT2/560264097a9b401730f6514 |  | 17hours21minutes
MX104: FST/SWTEST and Packout | MX104_FST_S_ | FST_S | FST_S | MX104 |  |  |  | 20220709.2226 | 8.17.0.19 | 14.1-20200226_mfg_141_psd.0 | ct0206 | Pass |  | /opt/JMTF/Logs/FXVN/2022/July/FST_SPARES/051670a8331631f077840a0 |  | 30 minutes
| MIC-MACSEC | FST_S | FST_S | MIC-MACSEC |  | 750-077332 | EAAC0744 | 20220726.0919 | 8.17.0.28 | 18.3-20181002_mfg_183_unified_prod.0 | CT0208 | Fail |  | /opt/JMTF/Logs/FXVN/2022/July/FST_SPARES/508137581a66902000516f0 |  | 22 minutes
| MIC-3D-20GE-EH | FST_S | FST_S | MIC-3D-20GE-EH |  | 750-046905 | EBAA8492 | 20220801.0936 | 8.17.0.30 | 14.1-20200226_mfg_141_psd.0 | ct0201 | Fail |  | /opt/JMTF/Logs/FXVN/2022/August/FST_SPARES/460269a816f950306538106 |  | 39 minutes and 7 seconds
| MX104_SWTEST_RE_MX_104 | SWTEST | SWTEST | MX104 | RE_MX_104 | MX104 | RB679 | 20220710.0334 | 8.17.0.19 | 20.4R3.8 | ct0206 | Pass |  | /opt/JMTF/Logs/FXVN/2022/July/SWTEST/17a7985760f834090508874 |  | 50 minutes
| MX104_PACKOUT_RE_MX_104 | PACKOUT | PACKOUT | MX104 | RE_MX_104 | MX104 | RB918 | 20220731.1342 | 8.17.0.30 |  |  | Pass |  | /opt/JMTF/Logs/FXVN/2022/July/PACKOUT/4519254a207990504f30796 |  | 25s
EX9200 | EX9214__ |  | SAT | EX9214 |  | EX9214 | JN1274198RFA | 20220716.2216 | 8.17.0.23 | JUNOS-64-15.1-20190509_mfg_15q1_gld.0 |  | Pass |  | https://fvnmfg1.juniper.net/jmtf_logs/FXVN/2022/July/SAT/4747710a84156a500504f49/ |  | 9.49
| EX9214__ |  | RIT | EX9214 |  | EX9214
| EX9214__ |  | FST_S | EX9214 |  | EX9214
| EX9214__ |  | SWTEST | EX9214 |  | EX9214

## Platforms_issue summary
Item | Report Date | PR Number | Issue Description | Platform | TID | configuration | script version | Originator | Responsible | Status | PR Category | Comments
| 20220712.0139 |  | 2022/07/12 01:41:20 ERROR 5-Packout::CheckJunos] Unable to get the software version using Device manager service 2022/07/12 01:41:20 ERROR 5-Packout::CheckJunos] Error: 10009 - Unable to get the software version using Device manager service 2022/07/12 01:41:20 ERROR 5-Packout::CheckJunos] SubTest complete, status: Error | MX104 | PACKOUT | CHASSIS RB627 MX104 Y Pass MX104 MIDPLANE EBAC4214 750-062050 Y Pass MX104 PEM0 1H070510100 740-045932 Y Pass DC_Power_Entry_Module PEM1 1H070510337 740-045932 Y Pass DC_Power_Entry_Module RE0 EBAC3460 750-061985 Y Pass RE_MX_104 RE1 EBAC3412 750-061985 Y Pass RE_MX_104 FANTRAY0 CASC1182 711-049570 Y Pass Fan_Tray | 8.17.0.19
| 20220721.1754 |  | 2022/07/21 18:03:31 ERROR 3-CheckProcess::CheckTestProcessFlow] PIC0:1:3 Fail: 500005 - GBA MIC0:1: RIT is not run. for Part:750-046905 Serial:EAAC5475 But the same PN is shown the result PASSED althought just INFO 3 subtest | MIC-3D-20G-EH | FST_S | CHASSIS RB542 MX104 Y Pass MX104 MIDPLANE EBAC4713 750-062050 Y Pass MX104 PEM0 1H170490288 740-045933 Y Pass AC_Power_Entry_Module PEM1 1H170490287 740-045933 Y Pass AC_Power_Entry_Module RE0 EBAC3243 750-061985 Y Pass RE_MX_104 AFEB0 AFEB0-MX104 MX104-BUILTIN_AFEB Y Pass Forwarding_Engine_Processor FPC0 FPC0-RB542 MX104-BUILTIN_FPC Y Pass MPC_BUILTIN MIC0:0 EBAA8441 750-046905 Y Pass 3D_20x_1GE(LAN)_EH,SFP PIC0:0:0 PIC0EBAA8441 750-046905-BUILTIN_PIC Y Pass 10x_1GE(LAN)__EH_SFP PIC0:0:1 PIC1EBAA8441 750-046905-BUILTIN_PIC Y Pass 10x_1GE(LAN)__EH_SFP MIC0:1 EAAC5475 750-046905 Y Fail 3D_20x_1GE(LAN)_EH,SFP PIC0:1:2 PIC2EAAC5475 750-046905-BUILTIN_PIC Y Fail 10x_1GE(LAN)__EH_SFP PIC0:1:3 PIC3EAAC5475 750-046905-BUILTIN_PIC Y Fail 10x_1GE(LAN)__EH_SFP FPC1 FPC1-RB542 MX104-BUILTIN_FPC Y Pass MPC_BUILTIN FPC2 FPC2-RB542 MX104-BUILTIN_FPC Y Pass MPC_BUILTIN MIC2:0 MIC0FPC2-RB542 MX104-BUILTIN_MIC Y Pass 4x_10GE(LAN)_SFP+ PIC2:0:0 PIC0MIC0FPC2-RB542 MX104-BUILTIN_PIC Y Pass 4x_10GE(LAN)_SFP+ FANTRAY0 EBAB7797 711-049570 Y Pass Fan_Tray | 8.17.0.25
| 20220726.0919 |  | 2022/07/26 09:25:55 WARN] RE0: Installed Version: 18.3-20181002_mfg_183_unified_prod.0 2022/07/26 09:25:55 WARN] RE0: Required Version: 14.1-20200226_mfg_141_psd.0 But MIC MACSEC just able to online with JunOS version higher 18.1, if using 14.1 version still shown not respond MIC information | MIC-MACSEC | FST_S | 2022/07/26 09:42:16 ERROR] RE0: JUNOS software (and/or package) version did not check out after update 2022/07/26 09:42:16 ERROR] ServiceMgr: Unable to initialize service 2022/07/26 09:42:16 INFO] DeviceMgr service is not enabled | 8.17.0.28
| 20220801.0936 |  | Requirement of FST_S not need SFP and MIC already install fully, still shown error about port not Ready like below: 2022/08/01 10:17:20 INFO 28-JIT::Jit] PIC2:0:0: All PIC ports are up 2022/08/01 10:17:24 ERROR 28-JIT::Jit] Some ports are not ready 2022/08/01 10:17:24 ERROR 28-JIT::Jit] Some ports are not ready 2022/08/01 10:17:24 ERROR 28-JIT::Jit] FPC0 Fail: 401293 - Some ports are not ready 2022/08/01 10:17:24 ERROR 28-JIT::Jit] MIDPLANE Fail: 401293 - GBA FPC0: Some ports are not ready 2022/08/01 10:17:24 ERROR 28-JIT::Jit] CHASSIS Fail: 401293 - GBA FPC0: Some ports are not ready 2022/08/01 10:17:24 ERROR 28-JIT::Jit] | MIC-3D-20G-EH | FST_S | CHASSIS RB476 MX104 Y Fail MX104 MIDPLANE EBAC4156 750-062050 Y Fail MX104 PEM0 1H170490403 740-045933 Y Pass AC_Power_Entry_Module PEM1 1H170490454 740-045933 Y Pass AC_Power_Entry_Module RE0 EBAB2153 750-061985 Y Pass RE_MX_104 AFEB0 AFEB0-MX104 MX104-BUILTIN_AFEB Y Pass Forwarding_Engine_Processor FPC0 FPC0-RB476 MX104-BUILTIN_FPC Y Fail MPC_BUILTIN MIC0:1 EBAA8492 750-046905 Y Fail 3D_20x_1GE(LAN)_EH,SFP PIC0:1:2 PIC2EBAA8492 750-046905-BUILTIN_PIC Y Fail 10x_1GE(LAN)__EH_SFP PIC0:1:3 PIC3EBAA8492 750-046905-BUILTIN_PIC Y Fail 10x_1GE(LAN)__EH_SFP FPC1 FPC1-RB476 MX104-BUILTIN_FPC Y Pass MPC_BUILTIN FPC2 FPC2-RB476 MX104-BUILTIN_FPC Y Pass MPC_BUILTIN MIC2:0 MIC0FPC2-RB476 MX104-BUILTIN_MIC Y Pass 4x_10GE(LAN)_SFP+ PIC2:0:0 PIC0MIC0FPC2-RB476 MX104-BUILTIN_PIC Y Pass 4x_10GE(LAN)_SFP+ FANTRAY0 EBAB7684 711-049570 Y Pass Fan_Tray | 8.17.0.30