## 1. OIL
No. | Report date | Reporter | Functional-Area | Problem-Level | Model | Serial | Description | Progress | Juniper comment | FVN Owner | JNP Owner | Due Date | Status | Problem-Level creation | Customer-Risk Initial Value | Functional-Area | Status
1 | 2022-08-12 | Vinh Dao | Process | 1-CL1 or 3-IL1 | N/A |  | FVN escape I2C process in first mass run lot. The serious issue happened on MX2K-RE, SFB3, MPC11E, MPC7E... all products |  | The SNs has been send to team. I2C issue on Mass production G2 and G7 | PE-Kylerr |  |  | open | 1-CL1 or 3-IL1 | Critical | Process | open
2 | 2022-08-12 | Vinh Dao | Process | 4-CL3 or 5-IL3 | SFB3 | EBAC8829 | phy 23 failed, found U25401 pins no solder in one side |  |  | ME莫锡海 |  |  | open | 4-CL3 or 5-IL3 | Major | Component defect | under-analysis
3 | 2022-08-12 | Brue | NTF | 5-CL4 or 6-IL4 | MPC7E | EBAD6531 EBAD0340 EBAD0452 | 8/9: Check test history :test 1 time (FPC1) back DBG, DBG still failed: All port have flapped during test,suspected NTF,send to retest 8/11:PASS RIT,FST_S 8/10 |  |  | TE-Sarah |  |  | open | 5-CL4 or 6-IL4 | Minor | Test script | under-review
4 | 2022-08-12 | Brue | Process |  | MX2K-RE | EBAC9388 EBAC9360 EBAC9410 | DDR connector J12 (450-033174)open on PMB |  |  | ME莫锡海 |  |  | open |  |  | NTF | monitored
5 | 2022-08-12 | Brue | Process |  | MPC7E-MRATE | EBAD0343 EBAD0469 EBAD0538 EBAD0347 EBAD0531 EBAD0386 EBAD7438 EBAD6501 EBAE1464 EBAE1454 | 8/5:cty log show:Err[24] Getset Value exceeds limit suspect DIMM,Reassembly DIMM and board bootup normal. |  |  | PE-Kylerr |  |  | open |  |  |  | closed
6 | 2022-08-12 | Brue | Process |  | MPC7E-MRATE | EBAD0435 EBAE1537 EBAE1757 EBAE1563 | "8/10: cty log show:Err[24] Getset Value exceeds limit suspect DIMM, VI and found DIMM connector J13 450-054900 open,Resolder DIMM connector and board bootup normal." |  |  | ME莫锡海 |  |  | open
7 | 2022-08-15 | Brue | Process |  | 711-069466 |  | ICT RE find 6 pcs wrong conponent as below : EBAD7253 R26501 EBAC8907 RP2503 EBAC8913 R26165 EBAC7716 L38001 EBAD7232 R4562 EBAD7196 R26502 |  |  | ME莫锡海 |  |  | open
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24

## Meeting minutes
2022-08-15
1 | ICT | ICT station: Collect top solder location issue on 711- boards | Brue
2 |  | QE investigate the top solder issues. Why does those escape AIO to improve AOI? | Sunny