## cmwrap for G256
PN | Model name | Test station | Function in cmwrap | Details | Target add | Target Validation | cmwrap update status | Validation update status | Status | Detect issue during run cmwrap
All | All | All | Check test process flow | - Option 1: check follow PN, base on Golden(MPC/MIC LOAD or old silver), silver/UUT. - Option 2: show chassis hardware -> Group2/5/6 check follow FRUs (RE, CB, FPC, PIC, CHASSIS/MIDPLANE, FPM, ECM, FANTRAY, PEM), base on Golden(MPC/MIC LOAD or old silver), silver/UUT. |  |  | need to discuss in weekly meeting to clear process and diagram (need Vinson/Colin support about Golden/Silver) |  | On-going | -cmwrap ignore some cases -NOTEs for test process FRUs: RE: RE_FCT, RE_FCT2, RIT, FST_S, SWT CB: SCBTEST, RIT, FST_S, SWT BFT1, BFT2, SLT, FST_S, SWT FPC: FPCTEST, RIT, FST_S, SWT BFT1, BFT2, SLT, FST_S, SWT PIC: PICTEST, RIT, FST_S, SWT CHASSIS/MIDPLANE: SAT, FST_S, SWT FPM: SAT, FST_S, SWT ECM: FST_S, SWT FANTRAY: SAT, FST_S, SWT PEM: SAT, FST_S, SWT System: SAT, RIT, FST_S, SWT
All | All | All | Check test station over 365 days | [5 empty] | Close
All | All | All | Require retest FST_SPARES whenever any status without SWTEST pass after FST_SPARES pass (detect PACKOUT failure lead to waste time to retest FST_S and SWT in continuous pass ) | [5 empty] | Close
750-136059 | MPC7E-MRATE | All | Cover quantity FPC slots input in to chassis at all station is 5 |  | 2022-08-05 | 2022-08-05 |  | OK | Close
750-136059 | MPC7E-MRATE | All | Cover Junos should be use 17.4-20210211_mfg_174_unified_prod.0 (on RE 750-054758 RE-S-X6-64G) |  | 2022-08-05 | 2022-08-05 |  |  | Close
750-136059 | MPC7E-MRATE | All | Cover failure cause by MIDPLANE link pfe errors | show chassis fabric plane (suggest 10 times), if detect link pfe link errors -> block session test then let TE double check | 2022-08-13 | 2022-08-13 |  |  | On-going
750-136059 | MPC7E-MRATE | All | Cover failure occur in function Diagnostics::FctPacketStressTest | show chassis interfaces terse, if detect link down -> block session test then let TE double check | 2022-08-13 | 2022-08-13 |  |  | On-going
ECO -52911 | RE-S-X6-64G RE-S-X6-128G-LT EX9200-RE | All | Cover firmware 6.01 with RE rework cause by rework issue (show system firmware) | Apply for: 750-054758, 750-063458, 750-072923 | 2022-08-12 |  | -complete with check firmware on RE master |  | Close
ECO -52911 | RE-S-X6-64G RE-S-X6-128G-LT EX9200-RE | Manually upgrade | semi-auto upgrade firmware | reduce time to manually upgrade firmware |  |  |  |  | Open
750-063181 | MPC3E | FPCTEST (FCT) | Cover Junos should be use 14.1 on RE 740- |  |  |  |  | OK | Close | need modify notice to "use Junos … and RE 740-…"
Check CBs and RE need to have same PN
|  |  | Block list | FRUs silver fail, need to verify, not allowed PD use |  |  | fvn2: nfs/md/tmp/CmWrapper8X/Cmwrap |  | Close
|  |  | Control down rev | Check from mail, daily update |  |  | need to provide down rev soure to Eric (ask Colin) |  | On-going