## G2_5_6 tracking
Juniper Group 2-5-6 Tracking
| Ngày bắt đầu: | 2022-08-03
| Ngày báo cáo: | 2022-08-10 |  |  |  |  | 4 | 5 | 6 | 7 | CN | 2 | 3 | 4 | 5 | 6 | 7 | CN | 2 | 3 | 4 | 5 | 6 | 7 | CN | 2 | 3 | 4 | 5 | 6 | 7 | CN | 2 | 3 | 4 | 5 | 6 | 7 | CN | 2 | 3 | 4 | 5 | 6 | 7 | CN | 2 | 3 | 4 | 5 | 6 | 7 | CN | 2 | 3 | 4 | 5 | 6 | 7 | CN | 2 | 3 | 4 | 5 | 6 | 7
[7 empty] | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep
Owner | Receive | Items | Description | Update status | Start | Target date | time axis 2022-08-03 to 2022-11-19
Sarah | Juniper Tom | MX480 FANTRAY NON-I2C | add 1 function require scan CLEI code to SAT | 0808: validation on ERA done, wait for official release | 2022-07-06 | 2022-08-20 | 2022-08-10: validation on ERA done, wait for official release
[7 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
[7 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
[7 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Sarah | Vinson/Tom | Fix PC test station + OP + ID test |  | 0809: fixed TE, PC, under contacting with Tom to create OP ID test, put chassis + silver fixed | 2022-08-08 | 2022-08-13
[12 empty] | 1 | 1 | 1 | 1 | 1 | 1
[12 empty] | 2 | 2 | 2 | 1 | 1 | 1
[12 empty] | 1 | 1 | 1 | 1 | 1 | 1
Alex | Alex | Setup Label Hotbox NO + Console cable Name, Owner: |  |  | 2022-08-10 | 2022-08-11
Alex | Sarah | Print failed label to paste on product | Ask Colin/Vinson if TE can purchase NG label |  | 2022-08-08 | 2022-08-12
Kane | Eric | Improve cmwrap to check and operation | check "show system firmware" and block if it still is 4.26 | 0810: check RE0 done, need function for swap master for RE1 | 2022-08-08 | 2022-08-11
[12 empty] | 1 | 1 | 1 | 1
[12 empty] | 2 | 2 | 2 | 1
[12 empty] | 1 | 1 | 1 | 1
Kane | Eric |  | upgrade firmware 4.26 to 6.01 for RE-S-X6-64G , RE LMT, EX9200-RE2 (3 PN) | send to Eric Diagram | 2022-08-08 | 2022-08-15
[12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
[12 empty] | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1
[12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Sarah | Eric |  | MPC7-MRATE check Junos 17.4 2021 check the Qty is 5 and alternate | send to Eric Diagram | 2022-08-08 | 2022-08-11
[12 empty] | 1 | 1 | 1 | 1
[12 empty] | 2 | 2 | 2 | 1
[12 empty] | 1 | 1 | 1 | 1
Alex | Eric |  | - check test process: check theo group 2/5/6 and UUT (RE, CB, FPC,…) - Validtion cmwrap - List function cmwrap check on G2/5/6) | send to Eric file test process follow PN '- need to check which PN 711- in back-end test (FANTRAY EX9204)... ? | 2022-08-08 | 2022-08-15 | 2022-08-09: send
[12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
[12 empty] | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1
[12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Sarah |  |  | SOP instruction use test resoure | supernotes, Agile, winscp, Sharepoint, MIDI-10, Ticket, JOBs | 2022-08-07 | 2022-08-10
[11 empty] | 1 | 1 | 1 | 1
[11 empty] | 2 | 2 | 2 | 2
[11 empty] | 1 | 1 | 1 | 1
Luffy |  | Visual SOP translate | Visual SOP translate, then upload to test PC, create SOP to training OP | - Translate SOP done - Sarah review on 0811 then Luffy upload to test PC | 2022-08-02 | 2022-08-12
[7 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
[7 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1
[7 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Luffy/ Alex/ Orange/ Hana/ Kane | Sarah | Apply supernotes and internet mail | apply and check after 5,10 days | -Orange/Hana done -Kane/Alex: apply internet mail -Luffy: supernotes | 2022-08-08 | 2022-08-09
[12 empty] | 1 | 1
[12 empty] | 2 | 2 | 2
[12 empty] | 1 | 1
Sarah | Juniper Tom | Shipable Junos Validation | 5 RE: | 0809: still not done: RE-MX2008, | 2022-08-01 | 2022-08-08
[7 empty] | 1 | 1 | 1 | 1 | 1 | 1
[7 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
[7 empty] | 1 | 1 | 1 | 1 | 1 | 1
Sarah/Orange | Juniper | Update firmware RE (MX and EX) | - find the way to update - feedback to CFT team | -MX done, - 0809: EX under validation | 2022-08-08 | 2022-08-15 | 2022-08-10: validation Sword instruction
[12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
[12 empty] | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1
[12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Sarah | Juniper Tom | SRX-IOC3 failed on SO config slot 0 |  | 0807: waiting mail confirm from Tom and then notice to PD to retest 0810: fix, wait test result | 2022-08-08 |  | 2022-08-11: need to ask Tom
[12 empty] | 2 | 2 | 2
Sarah | Juniper Tom | Report RE heatsink validation | work with Hana | validation under RIT station complete, need send result to Juniper Tom | 2022-08-06 | 2022-08-08 | 2022-08-11: need send log to Tom
[10 empty] | 1 | 1 | 1
[10 empty] | 2 | 2 | 2 | 2 | 2
[10 empty] | 1 | 1 | 1
Sarah | all Juniper team | Update DEV/ECO meeting minutes week 31 | save in Hugo computer |  | 2022-08-08 | 2022-08-08
1
[12 empty] | 2 | 2 | 2
1
Sarah | Vinson | Weekly report |  |  | 2022-08-12 | 2022-08-12
1
1
1
Sarah | Juniper Tom | update ERA Validation progress | work with team |  | 2022-07-08 | 2022-08-12
[7 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
[7 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1
[7 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Alex/Kane | Vinson | Hotbox validation |  |  | 2022-07-13 | 2022-08-16 | 2022-08-10: Hotbox 6
[7 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
[7 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1
[7 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Hana | Sarah | Setup 5 chassis MX240/480 test FCT + 1 rack of 4 chassis MX240 RIT |  | - Available: Setup 5 chassis MX240/480 test FCT + 1 rack of 4 chassis MX240 RIT (15 USB for FCT, 11 USB image) - 1 chassis need 4 USB test in 1 hour * 5 = 20USB + 10 USB image - If setup more => lacking AC cable
[7 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Sarah | Flank | ORT G2 validation
[7 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
[7 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
[7 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
[7 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
[7 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
[7 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
[7 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2